## Dashboard
RealWaste Deep Learning Project Control Center
Project title | Robust Real-World Waste Classification using Custom CNN Architectures and Transfer Learning
Deadline horizon | 10 days
Current gate | Gate 0 — Setup
Core experiments | E1 SimpleCNN ¦ E2 MultiScaleCNN ¦ E3 EfficientNet-B0
Optional experiment | E4 MultiScaleCNN without augmentation
Primary runtime | Google Colab
Storage | Shared Google Drive
Code | GitHub
Seed | 42
Image size | 224 × 224
Split | 70 / 15 / 15 stratified
Rule | Do not train before Gate 1 Dataset Audit PASS

## 10-Day Plan
Day | Primary Objective | Required Outputs | Gate/Freeze | Owner(s) | Status | Blocker/Notes
1 | Setup + Dataset Audit | Repo/Drive/Colab; class counts; corruption/dimension checks; sample grid | Gate 1 | Data Lead + Integration | Not Started
2 | Freeze split + SimpleCNN E2E | split.csv; shared dataloaders; E1 train/save/load/evaluate | Gate 2 | Data Lead + SimpleCNN | Not Started
3 | Freeze E1 + implement E2 | E1 final baseline; curves; E2 implementation | E1 Frozen | Simple/Complex Leads | Not Started
4 | Train/fix E2 | E2 stable run; architecture diagram | E2 Ready | Complex Lead | Not Started
5 | E3 transfer learning | EfficientNet head training; Stage A checkpoint | 3 models runnable | Transfer Lead | Not Started
6 | Fine-tune E3 + consolidate | Stage B; E1-E3 validation; report model sections | Core validation complete | Transfer/Eval + all | Not Started
7 | Final core experiments | Final E1-E3 test; optional E4 | CODE FREEZE | All | Not Started
8 | Analysis | Comparison table; confusion; per-class; error analysis | RESULT FREEZE | Evaluation + all | Not Started
9 | Report completion | Report >=90%; figures/tables inserted | Report gate | All | Not Started
10 | QA + presentation | Fact check; final report; slides; rehearsal | SUBMIT READY | All | Not Started

## Experiment Runs
Experiment ID | Run ID | Model | Seed | Batch | Optimizer | LR | Epochs Planned | Epochs Done | Augmentation | Class Weighting | Best Epoch | Best Val Metric | Checkpoint | Train Time (min) | Git Commit | Status | Notes
E1 |  | SimpleCNN | 42 | 32 |  |  | 30 |  | Standard | TBD after audit | [5 empty] | Not Started
E2 |  | MultiScaleCNN | 42 | 32 |  |  | 40 |  | Standard | TBD after audit | [5 empty] | Not Started
E3 |  | EfficientNet-B0 | 42 | 32 |  |  | 10 + 15 |  | Standard | TBD after audit | [5 empty] | Not Started
E4 |  | MultiScaleCNN | 42 | 32 |  |  | TBD |  | None | TBD after audit | [5 empty] | Optional | Augmentation ablation only if time permits

## Model Comparison
Experiment ID | Model | Accuracy | Macro Precision | Macro Recall | Macro F1 | Best Epoch | Params | Train Time (min) | Test Notes
E1 | SimpleCNN
E2 | MultiScaleCNN
E3 | EfficientNet-B0
E4 | MultiScaleCNN_NoAug

## Per-Class Metrics
Experiment ID | Class Name | Support | Precision | Recall | F1 | Notes

## Error Analysis
Experiment ID | Filepath | True Class | Predicted Class | Confidence | Failure Mode | Visual Note | Reviewer

## Risk Register
Risk | Severity | Trigger | Mitigation | Owner | Status
Scope creep | Critical | New model/task after Day 3 | Reject unless material validity fix | Integration Lead | Open
Data leakage | Critical | Different splits across models | One frozen split.csv | Data Lead | Open
Test-set tuning | Critical | Repeated test checks | Validation-only selection | Evaluation Lead | Open
Colab disconnect | High | Runtime reset | Save checkpoint/logs to Drive | Model Leads | Open
GPU unavailable | Medium | No Colab GPU | Kaggle backup using same repo/config/split | Integration Lead | Open
Report late | Critical | <50% by Day 7 | Write in parallel from Day 1 | All | Open

## Decision Log
ID | Date/Day | Decision | Reason | Evidence/Constraint | Owner | Status
D001 | Day 0 | Use RealWaste | 10-day deadline and assignment fit | Team decision | Team | Locked
D002 | Day 0 | Colab + Drive + GitHub | Avoid local compute burden | Time/compute constraint | Team | Locked
D003 | Day 0 | E1/E2/E3 core models | Maps to simple/complex/transfer requirements | Assignment requirement | Team | Locked
D004 | Day 0 | 70/15/15 stratified seed 42 | Fair reproducible comparison | Experimental validity | Team | Locked

## Deliverables
Deliverable | Required? | Owner | Due Day | Status | Evidence/Path | Notes
Dataset audit | Yes | Data Lead | 1 | Not Started
Frozen split.csv | Yes | Data Lead | 2 | Not Started
E1 SimpleCNN | Yes | Simple Lead | 3 | Not Started
E2 MultiScaleCNN | Yes | Complex Lead | 4 | Not Started
E3 EfficientNet-B0 | Yes | Transfer Lead | 6 | Not Started
Final evaluation | Yes | Evaluation Lead | 8 | Not Started
Error analysis | Recommended | All | 8 | Not Started
Report | Yes | All | 10 | Not Started
Slides | Yes | All | 10 | Not Started
Demo | Optional | TBD | 10 | Not Started |  | Drop if core work at risk